## Tabelle3
|  | 2018 |  | 2019 |  |  |  | 2020
| Tasks | 3/4 | 4/4 | 1/4 | 2/4 | 3/4 | 4/4 | 1/4 | 2/4
1 | Monitoring and Management Plan (pilote action)
1.1. | Preparation of visitor survey
1.2. | Conduction out of visitor survey (light barriers and human resources, ev. booklets of mountain tops)
1.3. | Data analysis and evaluation
1.4. | Rock Ptarmigan and ski tourism - Data Charging
1.5. | Data analysis and evaluation
1.6. | Questionnaire – Alpine huts and landlords
1.7. | Data analysis and evaluation
1.8. | Ski tour tourism booklet and estabish locally status quo
2 | Raising Awareness - locas and tourists (pilote action)
2.1. | Future dialoque I youth
2.2. | Future dialogue II stakeholder
2.3. | 10 Workshops "gemeinsam drüberschauen"
2.4. | Approval of the action plan
2.5. | Data analysis and evaluation
3 | Sustainable Tourism Action Plan
3.1. | Workshop on the spot
3.3. | Data analysis and evaluation
3.4. | Formal approval of the Action Plan